# Fund-Raising Development Plan

A development plan is crucial for your program’s success, particularly as it pertains to your fund raising and your budget.  Please review the attached sample development plan and consider working with your board to implement a similar plan in your organization.  It is important to make the plan as diversified as possible, including action steps for each strategy needed to accomplish the goal, and budget how much it will cost your program to raise the money.

### SAMPLE FUND-RAISING DEVELOPMENT PLAN

| ## Strategy | ## Goal | ## Action Steps | ## Ownership | ## When | ## Cost |
| --- | --- | --- | --- | --- | --- |
| #### New Member Acquisition | Goal: 500 new members-$9,000 | 1.Two direct mail campaigns to 10,000 prospects (300) 2. Each bd. member recruits 1 new member per month (120) 3. Participants in raft trips become members (50) 4. Buyers of raffle ticket booths become members (30) | 1. Staff w/help of consultant 2. Board committee 3. Staff 4. Staff | 1. May & Sept. 2. Monthly 3. Summer 4. Fall | 1. $7,000 2. No cost 3. No cost 4. No cost |
| #### Renewals | Goal: 100 out of 154 (65%) - $2,000 | 1.Call last year’s lapsed members, asking them to renew 2. Do 3 mailings to current members, one month apart 3. Call lapsed members, asking them to renew | 1.Staff & volunteers 2. Staff 3. Staff & volunteers | 1. January 2. January to March 3. May | 1. $50 2. $400 3. $50 |
| #### Special Appeals | #### Goal: $2,000 | 1. Prepare a special appeal to all members 2.Prepare a follow-up request in 6 weeks | 1.Staff 2.Staff | 1.October 2.December | 1. $400 2. $100 |
| #### Special Events | #### Goal: $10,000 | 1.Hold a raffle which will generate money, educate the public and recruit members | 1.Board committee | 1. June to October | 1. $2,500 |
| #### Major Donors | Goals: $10,000 from 46 2 @ $1,000 6 @ $500 8 @ $250 30 @ $100 | 1. Research names of potential major donors (185) 2. Create a special donor club with special benefits 3. Schedule personal visits with as many of these people as possible to ask for money 4. When visits are not possible, write a personal letter | 1.Staff w/help of board 2. Staff 3. Staff & board 4. Staff & board | 1.Ongoing 2. Ongoing 3. Ongoing 4. Ongoing | 1. $500 |
| #### Corporations | #### Goals: $7,000 | 1. Talk with local businesses and ask them to sign on as “Friends” with a gift of $300 2. Send proposals out to selected corporations | 1.Staff & volunteers 2. Board committee | 1.June to July 2. May | 1. $100 2. $100 |
| #### Foundations | #### Goals: $15,000 | 1. Research & prepare a list of foundation prospects 2. Prepare and mail out proposals 3. Follow up | 1.Intern 2. Staff 3. Staff | 1.January 2. February to April 3. May to July | 1. No cost 2. $100 3. No cost |
|  | TOTAL POSSIBLE INCOME = $55,000 |  |  |  | TOTAL EXPENSE = $11,300 |

Data adapted from Pat Munoz & Liz Raisbeck, “How to Plan Your Fundraising Strategy,” Grassroots Fundraising Journal.” Chardon Press. January 1997.