ShareCare Faith in Action Planning Modules

October 2016 – September 2019 Plan

| GOALS | OBJECTIVES | RATIONALE | ACTION STRATEGY | TIME FRAME (Objectives) | ACCOUNTABILITY | FINANCIAL COSTS |
| --- | --- | --- | --- | --- | --- | --- |
| Sustaining and Engaging ShareCare’s volunteer base. | Recruit 75 volunteers, train and involve them in service and enrichment Secure and train new volunteer caregivers each year B. Strengthening Board membership 1. Recruit a full 18 member board. 2. Enhance the diversity of the board by seeking persons with a variety of experiences, backgrounds and skills. C. Strengthen our committee system. 1. Establish regular meetings. 2. Supplement committees with non board members for particular tasks as needed. (Auction and Bowling) | 1. Meet waiting list needs and new requests. 2. Acquaint Faith Groups with ShareCare services and volunteer needs The Board of Directors of an organization plays many important roles in furthering the purpose of the organization. i.e. planning for future, monitoring the current goals and objectives, etc. Committees are the work force of ShareCare. | 1. Church bulletins and presentations 2. Media 3. Coordinators 4. Volunteer Center 5. New Recruitment Materials and Strategies: Branding 1. Identify skills of potential board members. 2. Coordinate skills of board members with job description of committees. 3. Provide board orientation and retreat. 1. Committees will identify and recruit members as needed. 2. Committees will submit written reports - meetings. | On-Going | 1. Volunteer Caregivers Committee 2. Volunteer Coordinators 3. Executive Director 4. Program Coordinators All Board Members | Approx. $50.00 per new volunteer |
| D. Connect ShareCare to wider Lehigh Valley | 1. Increase our presence as a Lehigh Valley wide agency. 2. Interaction with other Lehigh Valley agencies. | Community needs to know ShareCare. | 1. Media Contacts 2. Speakers bureau 3. United Way 4. Volunteer Center 5. SVA 6. Marketing Materials - Branding 7. Use of Website | On-Going | 1. Marketing Committee 2. Executive Director 3. Board members 4. Program Coordinators | 2,500.00 |
| E.Continue the relationship with Faith in Action National Network | 1. Make use of support from Faith in Action National Network 2. Maintain membership with Faith in Action National Network | Being part of a larger Faith in Action National Network is invaluable. | 1. Review Materials with Board 2. Attend conferences | On-Going | Executive Director Program Coordinators | $120.00 annual dues |
| F. Recruit additional Faith Communities. | Increase the number of Faith Communities by adding 5 per year and or Community Partnerships | A working partnership with faith groups and or other groups benefits the entire community by creating a larger pool of volunteers | 1. Staff will develop a recruitment work plan. 2. Clergy contacts 3. Presentations to Faith Communities 4. Incorporate Health Ministry programs from congregations as a partner. 5. Develop a faith community recruitment brochure. 6. Website/Internet | On-going | 1. Volunteer Caregivers Committee 2. Executive Committee 3. Executive Director 4. Program Coordinators |  |
| G. Pursue Expansion of program in Bethlehem and the wider Lehigh Valley. | Meet the needs of carereceivers in Bethlehem and in the wider Lehigh Valley. | We are responding to on-going requests for help. | Use of additional program staff. | 3 years | 1. Executive Committee 2. Executive Director 3. Program Coordinators 4. Director of Development | Funded by Grants and the ShareCare Operating Budget: Approx: $105,000.00 |
| H. Market ShareCare more widely and effectively. | To prepare and circulate marketing materials. | ShareCare needs enhanced visibility in the Lehigh Valley. | 2. To practice regular communication with faith communities, i.e. bulletins, newsletters, etc. | On-Going | 1. Marketing and Development Committee 2. Director of Development 3. Executive Director 4. Program Coordinators | $2,000.00 (Community Awareness Budget) |
| I. Strengthen financial base of ShareCare | 1. To continue fund raising using effective means with proven track record. 2. Evaluate alternative strategies. | Support current programming and staffing as well as lay ground work for expansion. | 1. To research alternative strategies. 2. Evaluate current fund raisers. | 1, 2 & 4 On –Going | 1. Director of Dev. 2. Executive Director 3. Marketing and Development Committee. 4. Volunteer Caregivers Committee | Approx. $7,000.00 First Year |
| J. Support, challenge and encourage volunteers through continued education. | 1. Maintain 75% of our volunteer base2. Evaluate current programming for training, support and enrichment. | Long term health of ShareCare depends on a strong volunteer base. | 1. Retreat 2. Enrichment sessions (2) 3. Appreciation dinner | On-Going | 1. Volunteer Caregivers Committee 2. Executive Director | $5,000.00 |